## Requirements Traceability
Project |  | Project Manager
Website Launch |  | David Albert |  | Requirements Traceability Matrix Example
Contact |  | Date
555-555-5555 |  | Dec. 10, 2024
ID | Requirement Name | Requirement Description | Type of Requirement | Requirement Source | Priority Level | Potential Risks | Requirement Status | Requirement Owner | Acceptance Criteria | Test Cases | Objectives and Goals | Requested By | Dept. | WBS/Deliverable | Comments
1 | User Authentication | Enable secure login for users with unique credentials | Functional | Stakeholder Request | High | Unauthorized access, poor user adoption | In Progress | IT Team Lead | Users can log in and out securely | Test invalid login, password reset, and lockout scenarios | Improve platform security and user experience | Sam Heard | IT | 2.1
2 | Payment Integration | Implement payment gateway for seamless transactions | Functional | Market Analysis | High | Payment failures, loss of revenue | Not Started | Product Manager | Transactions are processed within 5 seconds | Test successful, failed, and duplicate payments | Enhance revenue stream and user convenience | Penny Wenn | Product Management | 3.2
3 | Data Backup Mechanism | Implement daily automatic backups of user data | Non-functional | Compliance Requirement | Medium | Data loss during recovery, increased storage cost | Completed | DevOps Engineer | Daily backups are accessible and restorable | Test backup scheduling, accessibility, and data recovery | Ensure data integrity and disaster recovery |  | IT
Free Related Templates
Business Requirements Document Template for Word
Product Requirements Document Template for Word
Requirements Gathering Template for Word

## Sheet1
User Authentication | Enable secure login for users with unique credentials | Functional | Stakeholder Request | High | Unauthorized access, poor user adoption | In Progress | IT Team Lead | Users can log in and out securely | Test invalid login, password reset, and lockout scenarios | Improve platform security and user experience
Payment Integration | Implement payment gateway for seamless transactions | Functional | Market Analysis | High | Payment failures, loss of revenue | Not Started | Product Manager | Transactions are processed within 5 seconds | Test successful, failed, and duplicate payments | Enhance revenue stream and user convenience
Data Backup Mechanism | Implement daily automatic backups of user data | Non-functional | Compliance Requirement | Medium | Data loss during recovery, increased storage cost | Completed | DevOps Engineer | Daily backups are accessible and restorable | Test backup scheduling, accessibility, and data recovery | Ensure data integrity and disaster recovery